## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 3368
|  | Actual: | 3688.25
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-02-01 08:30 | 2026-02-01 10:20 | Completed | 1.83 | 1.83 | 0 | 0 | 1ª Clase
2 | T0002/O | Other | ALL | Student | Attend lecture |  | 2026-02-05 10:40 | 2026-02-05 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | 2ª Clase
3 | T0003/M | Management | Student 3 | Manager | Make plans |  | 2026-02-06 15:30 | 2026-02-06 16:45 | Completed | 1.5 | 1.25 | 75 | 62.5 | Organización de la 1ª reunión del equipo
4 | T0004/O | Other | ALL | Manager | Attend work meeting |  | 2026-02-06 17:30 | 2026-02-06 18:50 | Completed | 1.25 | 1.33 | 62.5 | 66.5 | 1ª Reunión del equipo
5 | T0005/M | Management | Student 3 | Manager | Initialise repository |  | 2026-02-07 10:00 | 2026-02-07 11:30 | Completed | 1.75 | 1.5 | 87.5 | 75 | Iniciando el repositorio
6 | T0006/D | Development | Student 1 | Developer | Customise the starter |  | 2026-02-07 16:30 | 2026-02-07 20:00 | Completed | 3 | 3.3 | 75 | 82.5
8 | T0008/D | Development | Student 2 | Developer | Write report |  | 2026-02-08 10:15 | 2026-02-08 12:23 | Completed | 2 | 2.13 | 50 | 53.25 | Redacción plantillas y chartering report
11 | T0011/O | Other | ALL | Student | Attend lecture |  | 2026-02-09 08:30 | 2026-02-09 10:20 | Completed | 1.8333 | 1.8333 | 0 | 0 | Follow up 1
12 | T0012/O | Other | ALL | Student | Attend lecture |  | 2026-02-12 10:40 | 2026-02-12 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | Teoría 12/02
13 | T0013/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-12 22:00 | 2026-02-12 23:30 | Completed | 1.3 | 1.15 | 32.5 | 28.75 | Implementar S1 del student 3
14 | T0014/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-13 09:00 | 2026-02-13 11:00 | Completed | 1.3 | 2 | 32.5 | 50 | Implementar S1 del student 1
15 | T0015/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-15 11:00 | 2026-02-15 13:05 | Completed | 1.3 | 2.05 | 32.5 | 51.25 | Implementar S1 del student 4
16 | T0016/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-13 09:15 | 2026-02-13 12:30 | Completed | 2.3 | 3.25 | 57.5 | 81.25 | Implementar S1 del student 2
17 | T0017/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-13 15:00 | 2026-02-13 18:55 | Completed | 2.3 | 3.55 | 57.5 | 88.75 | Implementar S1 del student 5
18 | T0018/M | Management | ALL | Manager | Supervise task |  | 2026-02-16 08:30 | 2026-02-16 10:20 | Completed | 1.83 | 1.83 | 91.5 | 91.5 | Follow up 2
19 | T0019/O | Other | ALL | Student | Attend lecture |  | 2026-02-19 10:40 | 2026-02-19 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | Teoría 19/02
20 | T0020/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-22 13:30 | 2026-02-22 14:50 | Completed | 1 | 1.8 | 25 | 45 | Implementar validaciones para S1 del student 3
21 | T0021/M | Management | ALL | Manager | Supervise task |  | 2026-02-23 08:30 | 2026-02-23 10:20 | Completed | 1.83 | 1.83 | 91.5 | 91.5 | Follow up 3
22 | T0022/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-22 16:00 | 2026-02-22 18:15 | Completed | 2 | 2.15 | 50 | 53.75 | Implementar validaciones para S1 del Student 4
23 | T0023/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-20 10:45 | 2026-02-20 14:45 | Completed | 4.5 | 4 | 112.5 | 100 | Implementar validaciones para S1 del Student 2
24 | T0024/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-20 09:00 | 2026-02-20 10:30 | Completed | 2 | 1.5 | 50 | 37.5 | Implementar restricciones grupales
25 | T0025/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-27 09:00 | 2026-02-27 15:00 | Completed | 4.5 | 6 | 112.5 | 150 | Populación de datos del Student 2
26 | T0026/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-23 15:30 | 2026-02-23 20:00 | Completed | 4.5 | 4.5 | 112.5 | 112.5 | Implementar validaciones para S1 del Student 5
27 | T0027/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-22 09:00 | 2026-02-22 10:15 | Completed | 1.5 | 1.25 | 37.5 | 31.25 | Implementar restricciones grupales
28 | T0028/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-23 08:30 | 2026-02-23 10:15 | Completed | 2 | 1.75 | 50 | 43.75 | Añadir dos cuentas de administrador
29 | T0029/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-04 17:00 | 2026-03-04 22:08 | Completed | 4.5 | 5 | 112.5 | 125 | Populación de datos del Student 5 (Sample y errata)
30 | T0030/O | Other | ALL | Student | Attend lecture |  | 2026-02-26 10:40 | 2026-02-26 12:30 | Completed | 0 | 0 | 0 | 0 | Teoría 26/02
31 | T0031/M | Management | ALL | Manager | Supervise task |  | 2026-03-02 08:30 | 2026-03-02 10:20 | Completed | 2 | 2 | 100 | 100 | Follow up 02/03
32 | T0032/D | Development | Student 1 | Developer | Implement feature
33 | T0033/M | Management | ALL | Student | Attend work meeting |  | 2026-03-04 16:00 | 2026-03-04 17:00 | Completed | 1 | 1 | 0 | 0 | Reunión de seguimiento del equipo
34 | T0034/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-05 15:30 | 2026-03-05 21:30 | Completed | 3 | 6 | 75 | 150 | Populación de datos S1
36 | T0036/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-04 17:00 | 2026-03-04 21:00 | Completed | 3.3 | 4 | 82.5 | 100 | Populación de datos S3
37 | T0037/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-04 14:15 | 2026-03-04 20:15 | Completed | 4 | 6 | 100 | 150 | Populación de datos Student 4
41 | T0041/O | Other | ALL | Student | Attend lecture |  | 2026-03-05 10:40 | 2026-03-05 12:30 | Completed | 2 | 2 | 0 | 0 | Clase de teoría 05/03
42 | T0042/M | Management | Student 2 | Student | Write report |  | 2026-03-05 12:30 | 2026-03-05 12:40 | Completed | 0.1 | 0.1 | 0 | 0 | Crear el contributing.txt
43 | T0042/O | Other | ALL | Student | Study and train |  | 2026-03-06 17:00 | 2026-03-06 17:45 | Completed | 0 | 0 | 0 | 0 | Upgrade REV 3
44 | T0043/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-06 17:00 | 2026-03-06 18:00 | Completed | 1 | 1 | 25 | 25 | Corregir fallo mínimo de los csv
45 | T0044/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-07 16:00 | 2026-03-07 20:00 | Completed | 3.5 | 4 | 87.5 | 100 | Listar campaigns como principal
46 | T0045/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-08 17:00 | 2026-03-08 19:40 | Completed | 3 | 2.3 | 75 | 57.5 | Listar strategies como principal
47 | T0046/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-20 16:00 | 2026-02-20 20:00 | Completed | 2 | 4 | 50 | 100 | Custom Validation del Student 1
50 | #REF! | Management | ALL | Manager | Supervise task |  | 2026-03-09 08:30 | 2026-03-09 10:20 | Completed | 2 | 2 | 100 | 100 | Follow up 09/03
51 | T0050/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-09 11:00 | 2026-03-09 15:00 | Completed | 3 | 2.5 | 75 | 62.5 | Listar strategies privadas como fundraiser
52 | T0051/D | Development | Student 2 | Developer | Implement feature |  | 2025-03-09 08:50 | 2025-03-09 10:15 | Completed | 1.5 | 1.42 | 37.5 | 35.5 | Corregir errores del follow up
53 | T0052/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-09 11:00 | 2026-03-09 13:00 | Completed | 2 | 2 | 50 | 50 | Listar campaigns privadas como spokesperson
54 | T0053/D | Development | Student 5 | Developer | Implement feature |  | 2025-03-09 16:50 | 2025-03-09 20:50 | Completed | 3.5 | 4 | 87.5 | 100 | Listar audit reports como principal
55 | T0054/D | Development | Student 5 | Developer | Implement feature |  | 2025-03-10 10:00 | 2025-03-10 12:00 | Completed | 2.5 | 2 | 62.5 | 50 | Listar audit reports privadas como auditor
56 | T0055/O | Other | ALL | Student | Attend lecture |  | 2026-03-12 10:40 | 2026-03-12 12:30 | Completed | 0 | 0 | 0 | 0 | Clase de teoría 12/03
57 | T0056/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-12 15:30 | 2026-03-12 19:00 | Completed | 4 | 3.5 | 100 | 87.5 | Operaciones CRUD como fundraiser
58 | T0057/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-09 16:30 | 2026-03-09 20:00 | Completed | 3 | 3.3 | 75 | 82.5 | Listar todas las invenciones como inventor
59 | T0058/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-13 18:00 | 2026-03-13 19:00 | Completed | 1.3 | 1 | 32.5 | 25 | Adquirir rol de fundraiser
60 | T0059/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-13 09:00 | 2026-03-13 14:00 | Completed | 4 | 5 | 100 | 125 | Operaciones CRUD como spokesperson
61 | T0060/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-13 18:30 | 2026-03-13 19:30 | Completed | 1.3 | 1 | 32.5 | 25 | Adquirir rol de Spokesperson como admin
62 | T0061/M | Management | ALL | Manager | Supervise task |  | 2026-03-16 08:30 | 2026-03-16 10:20 | Completed | 2 | 2 | 100 | 100 | Follow up 16/03
63 | T0062/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-09 15:20 | 2026-03-09 17:20 | Completed | 2 | 2 | 50 | 50 | Listar patrocinaciones privadas como patrocinador
64 | T0063/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-14 12:15 | 2026-03-14 19:00 | Completed | 5 | 6.45 | 125 | 161.25 | Operaciones CRUD como patrocinador
65 | T0064/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-15 17:00 | 2026-03-15 18:20 | Completed | 1 | 1.2 | 25 | 30 | Adquirir rol de patrocinador como admin
66 | T0065/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-15 18:30 | 2026-03-15 19:30 | Completed | 1 | 1 | 25 | 25 | Corregir fallos del validador del patrocinador
67 | T0066/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-15 15:00 | 2026-03-15 20:45 | Completed | 5 | 5.75 | 125 | 143.75 | Operaciones CRUD como auditor
68 | T0067/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-16 10:30 | 2026-03-16 11:15 | Completed | 1 | 0.75 | 25 | 18.75 | Adquirir rol de auditorcomo admin
70 | T0068/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-15 10:00 | 2026-03-15 11:30 | Completed | 2 | 1.5 | 50 | 37.5 | Listar secciones de auditoría privadas como auditor
71 | T0070/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-18 11:30 | 2026-03-18 12:30 | Completed | 1 | 1 | 25 | 25 | Corregir fallos del validador del auditor
72 | T0071/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-18 16:00 | 2026-03-18 18:00 | Completed | 2.5 | 2 | 62.5 | 50 | Comprobación de todo y algunas correcciones
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O